## Gantt Chart
TASK | PHASE | DATES | DAYS | JUNE |  |  |  | JULY
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1
|  |  |  | Jun 8-14 | Jun 15-21 | Jun 22-28 | Jun 29 - Jul 5 | 2006-07-01
Brainstorming | Planning | Jun 8 – Jun 10 | 3
Propose Concept Paper | Planning | Jun 11 – Jun 12 | 2
Finalizing the Title | Planning | Jun 13 | 1
Chapter 1 – Introduction & Background | Chapter 1 | Jun 14 – Jun 15 | 2
Chapter 1 – Statement of the Problem | Chapter 1 | Jun 16 – Jun 17 | 2
Chapter 1 – Significance & Definition of Terms | Chapter 1 | Jun 18 – Jun 19 | 2
Chapter 2 – Review of Related Literature | Chapter 2 | Jun 20 – Jun 21 | 2
Chapter 2 – RRL Matrix & Research Gap | Chapter 2 | Jun 22 – Jun 23 | 2
Chapter 3 – Research Design | Chapter 3 | Jun 24 – Jun 25 | 2
Submitting Request Letter to LGU | Requesting Data | Jun 24 - 29 | 6
Chapter 3 – System Architecture | Chapter 3 | Jun 29 – Jul 3 | 3
Received data | Arrival | June 24 - Jun 29 | 6
Proposal Defense | Defense | 2006-07-01 | 1